## Lagos House Price Project for S
S/N | Week | Working Session | Student Outcomes | Key Questions | Student Activity before this working session | Helpful Resources | Assessment
1 | 0 | Inaugural Session | Fork Git Hub Repo Understand Project Brief Understand basic troubleshooting tips | What problem are you solving? What type of ML problem is this? What ML algorithms can be used? Based on the structure of the site, what web scraping tools can be used? |  |  | None
2 | 1 | Week 1 working session | Understand basics of webscraping and possible tools Understand dynamic rendered sites and tools used to scrape them Understand how to setup complex forloops Resolve any issues encountered with scraping | Have you inspected the site? What challenges are you having scraping the site? What tools have you tried? | Review all the web scraping resources Commence Scraping the site | Web scraping Notebook | None
3 | 2 | Week 2 working session | Understand Algorithms which can solve the problem Identify relevant features Identify possible data pitfalls and challenges | What challenges are you having scraping the site? What tools have you tried? What features are you scraping and which do you think are most useful? | Review all the web scraping resources Finalise Scraping the site | Web scraping Notebook | Submit your web scraping code
4 | 3 | Week 3 working session | Identify key patterns based on EDA Understand how to identify outliers and treat them Treat missing values and outliers Develop base line model | What patterns did you notice in your data? Did you notice any missing values and outliers? What outliers have you identified and how did you deal with them? How did you convert your house price to int or float? | Review all the EDA and Data Preprocessing resources Treat missing values and outliers Build Baseline model | EDA notebook Data preprocessing notebook | Submit baseline model along with EDA and preprocessing steps
5 | 4 | Week 4 working session | Identify and extract new features from the data set Build an optimised model | What additional features can be extracted from the scraped data? How have you extracted these features? What additional features do you plan to extract? | Review all the Data manipulation and Feature engineering resources Create new features Build Optimised model | Data manipulation Notebook Feature engineering Notebook | None
6 | 5 | Week 5 working session | Identify and extract new features from the data set Build an optimised model | What challenges are you facing extracting features Why can't the model be improved to meet the specified RMSE | Review all the Data manipulation and Feature engineering resources Create new features Build Optimised model | Data manipulation Notebook Feature engineering Notebook | Submit optimised model
7 | 6 | Week 6 working session | Understand basic HTML and CSS concepts Understand basic dash concepts Search for dash templates and pick a dash template to work with based on the problem | WHat challenges do you have with HTML and CSS concepts What challenges do you have with dash concepts What chart elements are most suitable for the rent budget estimator? What template is most suitable for the rent budget estimator? | Review HTML, CSS and Dash resources Practice building chart elements | Dash Notebook HTML and CSS crashcourse | None
8 | 7 | Week 7 working session | Build chart elements in dash for project Resolve dash issues encountered | What challenges are you currently facing with HTML? What challenges are you currently facing with CSS? What challenges are you currently facing with Dash? | Review HTML, CSS and Dash resources Build chart elements for project Integrate ML model to app | Dash Notebook HTML and CSS crashcourse | None
9 | 8 | Week 8 working session | Finalise app for presentation day Build the final day presentation | What inputs should go into problem definition section What inputs should go into the solution section What inputs should go into challenges and recommendation section What inputs should go into Next steps section | Review HTML, CSS and Dash resources Build chart elements for project Integrate ML model to app | Dash Notebook HTML and CSS crashcourse | Dash app and slides for presentation day